## Slide 1: Agile Software Processes Assignment – Group BH

## Slide 2
Title :
Agile Practices in Action: Planning, Execution, and Metrics for a Mobile E-commerce App
Group BH :
REMYA. P. (2024TM)
SREERAAM K . (2024TM)
MADHURI PIDATALA(2024TM)
SHEFALI SRIVASTAVA(2024TM)
HARMALKAR RAHUL RAJAN SAYALI(2024TM93073)

## Slide 3
Introduction
Objective:
To simulate a project lifecycle using Agile methodologies, focusing on the development of a mobile e-commerce application.
Key Areas Covered:
Product Vision and Roadmap: Define the product's long-term goals and outline major milestones over a 6-month period, including three key releases.
User Stories and Backlog: Develop user-centric requirements using the INVEST criteria and create an initial product backlog with prioritized features and effort estimates.
Sprint Planning: Plan a two-week sprint by selecting user stories, defining tasks, and estimating effort, while aligning with team capacity and product goals.
Sprint Execution and Review: Simulate daily Scrum meetings, track progress with a burndown chart, and conduct a sprint review to assess completed work and gather feedback.
Metrics, Flow, and Communication: Analyze team performance metrics such as velocity, defect rate, and task flow management while proposing strategies for continuous improvement and effective communication.

## Slide 4
RoadMap

## Slide 5
User Stories

## Slide 6
Sprint Planning
Selected User Stories for the Sprint:
As a user, I want to add products to a shopping cart so I can view them before purchase.
  Story Points: 5
As a user, I want to modify quantities or remove items from my cart for more flexibility during purchase.
  Story Points: 8
As a user, I want a secure checkout process with multiple payment options to ensure trust and security.
  Story Points: 10
As a user, I want to receive a purchase confirmation via email to validate my order.
  Story Points: 7
Task Breakdown:
Add Products to Cart:
  Develop "Add to Cart" functionality (3 hrs)
  Update user interface for cart (4 hrs)
Modify/Remove Cart Items:
  Create item modification options (5 hrs)
  Backend update and synchronization (6 hrs)
Checkout Process:
  Integrate payment gateway (8 hrs)
  Security and data validation (5 hrs)
Order Confirmation Email:
  Develop email notification system (4 hrs)
  Integration with order database (3 hrs)
  Testing and email validation (4 hrs)
Sprint Goal:
Goal: Deliver a functional shopping cart and checkout system to enhance user purchasing capabilities.
Justification for User Story Selection:
Prioritization Basis: Selected user stories are high-priority items aligned with the product vision of delivering core e-commerce functionality.
Team Capacity: Based on a team velocity of 30 story points, the chosen stories fit within the capacity constraints, ensuring manageable workload distribution among four developers and one tester.

## Slide 7
Sprint Execution and Review
Sprint Completion Status:
Completed User Stories:
  Add products to a shopping cart (Story Points: 5)
  Modify and remove items from the cart (Story Points: 8)
  Secure checkout process with multiple payment options (Story Points: 10)
Incomplete User Story:
  Purchase confirmation email
  Reason for Non-Completion: Delayed due to dependencies on order database integration and additional testing requirements.
Stakeholder Feedback Summary:
Positive Feedback:
  Smooth shopping cart functionality, easy to use.
  Checkout process well-received for its security features and multiple payment options.
Improvement Areas:
  Stakeholders suggested enhancing the UI for the order summary screen to make it more user-friendly.
  Requested the addition of a progress indicator during the checkout process.
Proposed Scope Adjustments for Next Sprint:
Complete the pending "Purchase Confirmation Email" user story with additional testing and integration improvements.
Incorporate UI enhancements based on stakeholder feedback to improve the order summary screen and add a checkout progress indicator.
Plan and prioritize any new user stories derived from stakeholder suggestions, ensuring alignment with the overall product vision.

## Slide 8
Sprint Review
Sprint Completion Status:
Completed User Stories:
  Add products to a shopping cart (Story Points: 5)
  Modify and remove items from the cart (Story Points: 8)
  Secure checkout process with multiple payment options (Story Points: 10)
Incomplete User Story:
  Purchase confirmation email (Story Points: 7)
    Reason for Non-Completion: Delayed due to dependencies on order database integration and additional testing requirements.
Stakeholder Feedback Summary:
Positive Feedback:
  Smooth shopping cart functionality, easy to use.
  Checkout process well-received for its security features and multiple payment options.
Improvement Areas:
  Stakeholders suggested enhancing the UI for the order summary screen to make it more user-friendly.
  Requested the addition of a progress indicator during the checkout process.
Proposed Scope Adjustments for Next Sprint:
Complete the pending "Purchase Confirmation Email" user story with additional testing and integration improvements.
Incorporate UI enhancements based on stakeholder feedback to improve the order summary screen and add a checkout progress indicator.
Plan and prioritize any new user stories derived from stakeholder suggestions, ensuring alignment with the overall product vision.

## Slide 9
Sprint Retrospective
Retrospective Highlights:
Start Doing:
  Daily Pair Programming: Encourage developers to work together on complex tasks to improve code quality and reduce defects.
  Early Stakeholder Demos: Conduct mid-sprint demos with stakeholders to gather early feedback, minimizing major revisions later.
  Dedicated Blocker Resolution Meetings: Allocate short, focused meetings to quickly resolve blockers.
Stop Doing:
  Over-committing to Story Points: Avoid adding too many user stories to the sprint, which can lead to unfinished work.
  Multi-tasking Across Stories: Reduce switching between user stories to improve individual focus and task completion.
  Extensive Manual Testing: Shift towards automated testing to save time and improve accuracy.
Continue Doing:
  Daily Stand-Up Meetings: Maintain short, focused daily stand-ups to align on tasks and discuss blockers.
  Regular Code Reviews: Continue peer code reviews to ensure coding standards, knowledge sharing, and improved quality.
  Transparent Progress Tracking: Use tools such as task boards and burndown charts to visualize progress and adapt plans.
Expected Improvements for the Next Sprint:
Increased Team Efficiency: Pair programming and blocker resolution will accelerate task completion.
Enhanced Quality and Stakeholder Satisfaction: Early demos will ensure alignment with stakeholder expectations.
Focused Workflow: Reduced multi-tasking will lead to higher productivity and better story completion rates.

## Slide 10
Metrics Analysis
1. Velocity Trend Analysis:
Observed Trend Over 3 Sprints:
  Sprint 1,2,3 : All story points completed
Inconsistencies Identified:
  Slight fluctuations due to unexpected dependencies and scope changes.
Proposed Solutions:
  Improve Task Breakdown: Break down large stories into smaller, manageable tasks to enhance estimation accuracy.
  Buffer for Unplanned Work: Allocate a buffer for unforeseen tasks or urgent issues that may arise during sprints.
2. Defect Rate and Lead Time:
Defect Rate Analysis:
  Increased defects noted when new features were integrated without automated testing coverage.
Lead Time Evaluation:
  Longer lead times were observed due to delayed dependencies and testing cycles.
Improvement Suggestions:
  Implement Automated Testing: Increase coverage to detect issues earlier and reduce manual testing time.
  Adopt Continuous Integration (CI): Use CI pipelines to ensure that code changes are continuously built, tested, and integrated.
3. Task Flow Management Strategy:
Issue: Tasks getting stuck in "In Progress" due to unresolved dependencies.
Proposed Solutions:
  Swarming: Have team members collaborate to resolve blockers together quickly.
  Limit Work In Progress (WIP): Restrict the number of tasks being worked on at any given time to reduce bottlenecks.
  Enhanced Communication: Use daily stand-ups and additional check-ins focused on dependency resolution to ensure smooth task flow.

## Slide 11
Task Flow Management Strategy:
Scenario: Tasks stuck in "In Progress" due to unresolved dependencies.
Proposed Solutions:
  Swarming Technique: The team works collectively to resolve high-priority blockers, pooling expertise to speed up task completion.
  Limit Work In Progress (WIP): Enforce limits on the number of concurrent tasks to avoid bottlenecks and enhance focus.
  Effective Communication: Schedule focused discussions to address and clear dependencies quickly. Use daily stand-ups and ad-hoc sync meetings as needed.
Information Radiator Design:
Visual Components:
  Task Board: Clearly displays tasks in columns such as "To Do," "In Progress," "Blocked," and "Done."
  Burndown Chart: Tracks progress of completed story points over the sprint period, providing a visual cue on remaining workload.
  Dependency Tracker: Highlights tasks waiting on dependencies, ensuring blockers are prioritized.
Benefits of an Information Radiator:
Improved Transparency: All team members and stakeholders can see sprint progress at a glance, enhancing accountability.
Real-Time Updates: Enables quick course corrections and status alignment.
Enhanced Communication: Facilitates proactive discussions on blockers and progress during stand-ups and reviews, fostering collaboration and trust.
Task Flow Management

## Slide 12
Summary of Agile Practices Applied:
Product Vision and Roadmap Creation: Defined a clear vision and outlined major milestones to guide development.
User Stories and Backlog Management: Developed user stories using the INVEST criteria, prioritized backlog items, and estimated story points.
Sprint Planning and Execution: Conducted sprint planning, broke down tasks, and managed a simulated two-week sprint with daily stand-ups, burndown tracking, and progress monitoring.
Sprint Review and Retrospective: Assessed completed stories, gathered stakeholder feedback, and identified areas of improvement for future iterations.
Metrics Analysis and Flow Management: Analyzed velocity trends, defect rates, and task flow, proposing strategies to optimize productivity, communication, and quality.
Key Takeaways:
Adaptability: Agile enables teams to rapidly adapt to changes, ensuring that the product remains aligned with evolving stakeholder needs.
Collaboration: Effective communication, collaboration, and transparency are at the heart of Agile, leading to more cohesive team efforts and better outcomes.
Continuous Improvement: Agile’s iterative approach encourages regular assessment and refinement of processes, enhancing product quality and team performance over time.
Final Thought:
Agile Practices Drive Success: By applying Agile principles and metrics, teams can ensure their work is efficient, transparent, and aligned with business goals, resulting in a superior product and satisfied stakeholders.
Conclusion